## Sheet1
Mavin Manufacturing - ERP Implementation (Acumatica) | Start Date | End Date or Only Date
Business Case and Proposal | 2024-06-01 | 2024-06-30
Decision on Software and Implementation Vendor | 2024-07-01 | 2024-08-15
Assign Resources | 2024-09-01 | 2024-09-30
Internal Kickoff |  | 2024-10-15
Project Plan and Approval | 2024-10-01 | 2024-11-01
External Kickoff with Vendor Consultants |  | 2024-11-15
Discovery | 2024-11-20 | 2024-12-15
Master File Data Conversion |  | 2025-12-30
Team Training | 2025-01-02 | 2025-01-30
Solution Design/ Build Phase | 2025-01-30 | 2025-11-01
Full Data Conversion |  | 2025-05-05
Testing Phase | 2026-01-15 | 2026-03-15
Create Process Documentation | 2025-11-01 | 2026-01-02
End User Training | 2026-04-01 | 2026-05-01
Pilot | 2026-05-02 | 2026-06-10
Go No Go |  | 2026-06-15
Go Live |  | 2026-07-01